# Heartland Polymers: Strategic Development Plan

Effective Date: 2026-01-08. Next Review: 2026-05-08. Plan Owner: Supplier Relationship Manager, Crestview Industries.

## Background

Heartland Polymers is a strategic supplier in the raw materials category, with annual spend of $3.8M. Performance has been strong, with overall scores consistently above 87. This development plan tracks three growth targets agreed at the January 2026 strategic review.

## Improvement Targets

| Target | Goal | Deadline |
| --- | --- | --- |
| Delivery on-time rate | Increase from 87% to 94% | 2026-06-30 |
| Defect rate | Reduce from 2.1% to below 1.0% | 2026-09-30 |
| Supplier portal adoption | Increase from 40% to 100% | 2026-09-30 |

## Milestones

| Milestone | Target Date | Status |
| --- | --- | --- |
| Joint quality review and root cause workshop | 2026-02-15 | Complete |
| Portal training for 100% of Heartland sales staff | 2026-04-01 | Complete |
| Mid-year review | 2026-05-08 | Pending |
| Defect rate validation in incoming inspection | 2026-08-01 | Pending |

## Quarterly Check-In Notes

Q4 2025: Delivery on-time rate at 91%. Defect rate at 1.6%. Portal adoption at 55%.

Q1 2026: Delivery on-time rate at 93%. Defect rate at 1.4%. Portal adoption at 72%.